## Sheet1
11/06-11/19 - User Stories | Task | Story Points | Checkout | Status | sprint backlog | Ready | In-Progress | Done | Finish Date
1. As a developer I want LocSilenece to Temporarily modify the phones volume setting | Incorporating volume system to recursive task | 3 | Thomas | done |  |  |  | x
| Making notification non-removable | 1 | Alon | done |  |  |  | x | 2017-11-28
| Prevent locSilence from overwriting manual user changes | 2 | Rami | ready |  |  |  | x | 2017-11-28
| Revert back to original volumes UNLESS user changed volume while locSilence was working | 2 | Rami | ready |  | x
| Figure out equation for finding the distance from current location to custom radius location | 3 | Erik | in-progress |  |  | x
| integrate user inputted generic radius to drawable circle | 1 | Erik | done |  |  |  | x | 2017-11-29
2. As the user I want to have my app look beautiful and intuitive to use | LocSettings UI Overhaul | 2 | Thomas | done |  |  |  | x | 2017-11-25
| Saved Location UI Overhaul | 2 | Thomas/Rami | done |  |  |  | x | 2017-11-25
| Add Locations UI Overhaul | 2 | Thomas/Rami | done |  |  |  | x | 2017-11-25
| Add delete button to saved location item | 1 | Thomas | done |  |  |  | x | 2017-11-25
| Integrate app icon | 2 | Thomas | done |  |  |  | x | 2017-11-28
| swap searchActivity searchbar into map activity when fab hit | 3 | Alon | in-progress |  |  | x
| Add help page | 1 | Thomas | ready |  | x
| Fix app naming (right now, Map is the name of the app not LocSilence) | 1 | Thomas | done |  |  |  | x | 2017-11-29
| custom searchbar for LocList which only shows locations in db | 3 | Rami | ready |  | x
| Fix map and list activity stack behavior (animation) | 1 | Any | in-progress |  | x
3. As the user I want to visually see which locations will be altered by LocSilence. | Adding pins to saved location/showing red dot | 5 | Alon/Erik | done |  |  |  | x | 2017-11-25
| Fix map activity to have the correct button to bring map to current location | 1 | any | ready
| Give user ability to set a generic radius in the location settings | 1 | Thomas | done |  |  |  | x | 2017-11-26
| Implement 8 point drawing in settings map | 5 | Erik | done |  |  |  | x | 2017-11-29
| Integrate 8 point draw into settings and implement gson in db | 5 | Rami plz halp | ready |  |  | x
| implement back button in customMapProximity for popping points off the polygon | 2 | Thomas | done |  |  |  | x | 2017-11-29
| show custom proximities on the map activity | 1 | Erik | blocked (need gson in db)
4. Testing | Unit Testing | 8 | Any | not started |  | x
| Real world testing | 5 | Rami | in-progress |  |  | x
5. As the user I want my locations to come up with previous settings that I set for the locations when I edit it | Load context when editing location | 2 | Thomas | done |  |  |  | x | 2017-11-25
| GSON Implementation of storing volumes in the db | 1 | Thomas/Rami | not started |  | x
6. As a user I want locSilence to be efficient and not cpu intensive | Storing last silenced location and checking every recursive call | 1 | Rami | done |  |  |  | x
| Limit num locations | 2 | Thomas | done |  |  |  | x | 2017-11-28
7. As the developer I want clean code | Rename classes | 1 | Rami | done |  |  |  | x | 2017-11-28
2017-11-28