## Sheet1
10/24-11/05 - User Stories | Task | Story Points | Checkout | Status | sprint backlog | Ready | In-Progress | Done | Finish Date
| Add fix for duplicate keys in db | 2 | Rami | done |  |  |  | x | 2017-10-25
1. As a user I want to intuitively see which locations have been silenced through a visualization on the mapView. | Implement basic map view outline locs which are silence | 8 | Erik | done |  |  |  | x | 2017-11-04
2. As a user I want my phone to be silenced for the locations that I have selected. | Implement architecture for repeatedly pinging phone location | 2 | Rami | done |  |  |  | x | 2017-10-27
| Implement math for determining if phone is within silencing radius | 8 | Rami | done |  |  |  | x | 2017-11-04
| Pull location from db and apply settings when entering silence loc | 2 | Rami | done |  |  |  | x | 2017-11-04
| volume returned to its original state after leaving a selected location | 1 | Rami | done |  |  |  | x | 2017-11-04
3. As a user I want to know when my phone volume is being altered by LocSilence. | Temporary notification when phone is being altered | 5 | Alon | done |  |  |  | x | 2017-10-29
4. As a user I want more control over what types of volumes will be altered, and to what volume. | Add UI for different volume settings to addLocation page | 3 | Thomas | done |  |  |  | x | 2017-10-28
| Add new volume controls to DB | 2 | Thomas | done |  |  |  | x | 2017-11-03
| Connect new volume data to be automatically applied | 1 | Thomas | done |  |  |  | x | 2017-10-28
5. As a user I would like the ability to turn LocSilence’s services on and off, so that my volume will not be altered and I can save battery life. | Add ui for turning Services completely on or off | 5 | Alon | done |  |  |  | x | 2017-10-29