## Sheet1
10/9-10/22 | Task | Story Points | Checkout | Status | sprint backlog | Ready | In-Progress | Done | Date Done
| Preparation -- Explore maps API | 2 | All | done |  |  |  | x | 2017-10-12
| Get comfortable with android studio | 5 | Thomas | done |  |  |  | x | 2017-10-12
| Create project with google maps template/make first commit | 1 | Rami | done |  |  |  | x | 2017-10-09
| Implement sliding out taskbar | 1 | Erik | done |  |  |  | x | 2017-10-12
| Add google search api location input bar (from maps API) | 3 | Alon | done |  |  |  | x | 2017-10-19
| set up Local SQL db (on phone) | 1 | Rami | done |  |  |  | x | 2017-10-14
| Write search result to database | 3 | Thomas | done |  |  |  | x | 2017-10-21
| Create view swap button | 5 | Alon | done |  |  |  | x | 2017-10-15
| Create listview page | 2 | Alon | done |  |  |  | x | 2017-10-15
| pull addresses from DB to listview | 3 | Rami | Ready |  |  |  | x | 2017-10-21
| Research map view outline locs which are silenced | 2 | Erik | Ready |  |  |  | x | 2017-10-22
| Fix up UX | 1 | Rami | Ready |  |  |  | x | 2017-10-18
| Research silencing implementation | 2 | Rami | Ready |  |  |  | x | 2017-10-22
| Total | 31